## ENTREGABLES
objetivo: | lograr la implementación de todo el programa en 8 meses
quien va a ganar: | menor costo
1 | Tablero donde se vea el plan de trabajo general inicio - fin del programa
2 | tablero donde se vea el plan de trabajo por site
3 | tabla de uso de recursos por sitio y general para el programa. Quiero poder modificar esa tabla
4 | poder guardar el escenario
5 | que me de un resumen de costos para el programa (por escenario), costo por site, por tipo de recurso
rubrica de calificación |  | Maxima | Ejemplo
|  | 100% | 84.38%
| 8 meses + menor costo | 50% | 50%
| Rúbrica | 50% | 34.38%
|  | Maxima | Ejemplo
| Dashboard principal | 4 | 2
| Guardar y comparar escenarios | 4 | 3
| Explicacion y entendimiento de cada pestaña del excel | 4 | 3
| Calidad de la información. Correcta, bien etiquetada, sin basura ni errores. | 2 | 1
| Visual / UI. Limpio, con jerarquía y legible. | 2 | 2
|  | 16 | 11
|  | 50% | 34.38%

## Sites Master
Country | Brewery | Cluster | Capacity (Mio HL) | Production (Mio HL) | Distribution Volume (K HL) | Line Capacity | Production Lines | # Warehouses | Warehouse Area | Occupation LV | Aisles Identification | Box Identification | Control Tower | T2/MKP/KA | Forklifts in Logistics | HC Forklifts | WIFI State | Tablets | Counting Devices
Mexico | Site 01 | 2 | 3.72 | 1.43 | 6400 | 38.44% | 3 | 1 | 9100 | 81.5% | 89% | Yes | No | No | 18 | 38 | 85% | 15 | 5
Mexico | Site 02 | 2 | 6.46 | 4.77 | 11160 | 73.84% | 6 | 2 | 15572 | 94% | 0% | No | No | No | 30 | 90 | 0% | 29 | 6
Mexico | Site 03 | 2 | 6.46 | 4.77 | 11160 | 73.84% | 6 | 2 | 15572 | 94% | 0% | No | No | No | 30 | 90 | 0% | 29 | 6
Mexico | Site 04 | 2 | 6.59 | 4.58 | 11520 | 69.5% | 5 | 2 | 17742 | 78% | 0% | No | Yes | No | 37 | 80 | 0% | 15 | 4
Mexico | Site 05 | 3 | 2.75 | 2.12 | 6848 | 77.09% | 2 | 3 | 5239 | 85.5% | 90% | Yes | No | Yes | 14 | 42 | 0% | 14 | 4
Mexico | Site 06 | 1 | 13.2 | 12.19 | 29946 | 92.35% | 9 | 2 | 36333 | 100% | 93% | Yes | Yes | Yes | 76 | 213 | 0% | 85 | 8
Mexico | Site 07 | 2 | 4.77 | 3.82 | 9900 | 80.08% | 4 | 1 | 14897 | 105% | 0% | No | No | Yes | 32 | 75 | 0% | 32 | 6
Colombia | Site 08 | 1 | 14.2623 | 14.2215 | 11189 | 99.71% | 3 | 1 | 28576 | 104% | 100% | Yes | Yes | Yes | 32 | 117 | 100% | 40 | 5
Colombia | Site 09 | 2 | 7.9589 | 3.0929 | 1822.3038 | 38.86% | 4 | 1 | 14097 | 88% | 50% | Yes | Yes | Yes | 10 | 32 | 70% | 20 | 4
Colombia | Site 10 | 1 | 13.6895 | 10.3165 | 11164.5596 | 75.36% | 10 | 4 | 13978 | 96% | 80% | No | Yes | Yes | 62 | 169 | 50% | 55 | 7
Colombia | Site 11 | 3 | 3.9804 | 3.4123 | 2911.3283 | 85.73% | 4 | 3 | 4684 | 84% | 80% | No | No | No | 17 | 42 | 60% | 16 | 3
Colombia | Site 12 | 4 | 2.1682 | 0.72308 | 699.0703 | 33.35% | 2 | 1 | 3797 | 80% | 80% | No | No | No | 4 | 15 | 70% | 5 | 3
Colombia | Site 13 | 1 | 30.3682 | 20.9553 | 23650.2134 | 69% | 14 | 2 | 85322 | 108% | 80% | Yes | Yes | Yes | 100 | 345 | 60% | 135 | 15
Colombia | Site 14 | 1 | 13.6373 | 10.6181 | 11442.7306 | 77.86% | 11 | 1 | 69016 | 88% | 80% | No | Yes | No | 52 | 166 | 50% | 60 | 6
Colombia | Site 15 | 2 | 5.0028 | 4.509 | 4946.467 | 90.13% | 5 | 3 | 9601 | 105% | 60% | No | Yes | No | 19 | 54 | 70% | 18 | 4

## Financials (USD)
Country | Brewery | Benefits per month | Implementation Costs | Devices | Forklift Structure | Warehouse Signage | Labels | Costs without Labelers & WiFi | Label Printers / Labelers | Manual Labeling | WiFi Full | WiFi Full Optimized | WiFi Prioritized
Mexico | Site 01 | 18511 | 15000 | 0 | 6668.7957 | 11370.3713 | 14425.1534 | 47464.3204 | 7144.76 | 0 | 44451 | 43451 | 0
Mexico | Site 02 | 26878 | 15000 | 70212.869 | 9262.2162 | 27796.938 | 21152.7918 | 143424.8151 | 81930.072 | 142702.7027 | 287249 | 220687 | 110343.5
Mexico | Site 03 | 61087 | 25000 | 84255.4429 | 11114.6595 | 23591.8332 | 18886.4213 | 162848.3568 | 212307.9 | 259459.4595 | 378909 | 157740 | 112671.4286
Mexico | Site 04 | 70898 | 25000 | 103915.0462 | 13708.0801 | 44202.7663 | 19286.8134 | 206112.706 | 184000.18 | 220540.5405 | 411279 | 368914 | 230571.25
Mexico | Site 05 | 14809 | 15000 | 0 | 5927.8184 | 10505.1615 | 11709.5812 | 43142.561 | 73600.072 | 103783.7838 | 219880 | 206497 | 77436.375
Mexico | Site 06 | 76636 | 35000 | 213447.1219 | 28157.1374 | 43677.8758 | 49482.4237 | 369764.5588 | 302730.288 | 376216.2162 | 523835 | 297466 | 220345.1852
Mexico | Site 07 | 30543 | 25000 | 98298.0167 | 12967.1028 | 39945.6344 | 13220.4949 | 189431.2487 | 147200.144 | 181621.6216 | 277152 | 123137 | 94720.7692
Colombia | Site 08 | 70420 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0
Colombia | Site 09 | 15920 | 15000 | 0 | 3600 | 12547 | 3600 | 34747 | 0 | 0 | 133781 | 115803 | 100862
Colombia | Site 10 | 90320 | 25000 | 0 | 15600 | 57883 | 8100 | 106583 | 308459.6755 | 0 | 487872 | 364795 | 154945.835
Colombia | Site 11 | 24480 | 15000 | 0 | 5560 | 15273 | 4500 | 40333 | 176263 | 0 | 180753 | 185549 | 94573.8118
Colombia | Site 12 | 10180 | 5000 | 0 | 1440 | 3746 | 1800 | 11986 | 88131 | 0 | 116598 | 73392 | 43642.3158
Colombia | Site 13 | 109140 | 50000 | 369489 | 44000 | 73532 | 20700 | 557721 | 1189773 | 0 | 333663 | 267903 | 136549.4177
Colombia | Site 14 | 56820 | 35000 | 0 | 18560 | 58580 | 9000 | 121140 | 925379 | 0 | 319639 | 286043 | 121496.1046
Colombia | Site 15 | 27560 | 15000 | 0 | 5320 | 20351 | 3600 | 44271 | 88131 | 0 | 139767 | 134417 | 79930.6351

## Resource Master
Role | Work Mode | Can Multitask | Internal or External | Fixed or Flexible Cost | Average Monthly Cost (MXN) | Actual | Escenario 1
Solution Architect | Remote | Yes | Internal | Fixed | 36000 | 1 | 5 | Go Live | Post
Warehouse Manager Org A | Hybrid | Yes | Internal | Fixed | 35000 | 1 | 5
Project Manager Country B | Hybrid | Partial | Internal | Fixed | 25000 | 1 | 5
Project Manager Country A | Hybrid | Partial | Internal | Fixed | 25000 | 1 | 5
Change Management Lead | Onsite | No | Internal | Fixed | 16000 | 1 | 5
Change Management Lead | Onsite | No | External | Fixed | 16000 | 1 | 5
Infrastructure Lead | Onsite | No | Internal | Fixed | 42000 | 1 | 5
Infrastructure Lead | Onsite | No | External | Flexible | 43000 | 1 | 5
Functional Lead | Onsite | No | Internal | Fixed | 35000 | 1 | 5
Functional Lead | Onsite | No | External | Flexible | 35000 | 1 | 5
SAP Integrations Lead | Remote | Yes | Internal | Fixed | 62000 | 1 | 5
SAP Integrations Specialist | Remote | Yes | Internal | Flexible | 55000 | 1 | 5
Azure Lead | Remote | Yes | Internal | Fixed | 48000 | 1 | 5
Azure Specialist | Remote | Yes | Internal | Flexible | 45000 | 1 | 5
Testing Lead | Remote | Partial | Internal | Flexible | 35000 | 1 | 5
Trainers | Onsite | No | External | Flexible | 28000 | 1 | 5
Functional Lead Vendor A | Remote | Yes | External | Flexible | 36000 | 2 | 5
Support Lead | Remote | Yes | External | Flexible | 22000 | 2 | 5

## Implementation Phases
Cluster | Phase | Sequence | Deployment Maturity | Duration in Weeks
1 | Site Readiness | 1 | A | 5
1 | Design Adaptation | 2 | A | 2
1 | Functional Review | 3 | A | 1
1 | UAT | 4 | A | 2
1 | Training | 5 | A | 3
1 | DIALT | 6 | A | 1
1 | Go Live | 7 | A | 1
1 | Hypercare | 8 | A | 4
2 | Site Readiness | 1 | A | 4
2 | Design Adaptation | 2 | A | 1
2 | Functional Review | 3 | A | 1
2 | UAT | 4 | A | 2
2 | Training | 5 | A | 2
2 | DIALT | 6 | A | 1
2 | Go Live | 7 | A | 1
2 | Hypercare | 8 | A | 4
3 | Site Readiness | 1 | A | 4
3 | Design Adaptation | 2 | A | 1
3 | Functional Review | 3 | A | 1
3 | UAT | 4 | A | 1
3 | Training | 5 | A | 2
3 | DIALT | 6 | A | 1
3 | Go Live | 7 | A | 1
3 | Hypercare | 8 | A | 4
4 | Site Readiness | 1 | A | 2
4 | Design Adaptation | 2 | A | 0
4 | Functional Review | 3 | A | 1
4 | UAT | 4 | A | 1
4 | Training | 5 | A | 1
4 | DIALT | 6 | A | 1
4 | Go Live | 7 | A | 1
4 | Hypercare | 8 | A | 3
1 | Site Readiness | 1 | B | 4
1 | Design Adaptation | 2 | B | 1
1 | Functional Review | 3 | B | 1
1 | UAT | 4 | B | 1
1 | Training | 5 | B | 2
1 | DIALT | 6 | B | 1
1 | Go Live | 7 | B | 1
1 | Hypercare | 8 | B | 4
2 | Site Readiness | 1 | B | 4
2 | Design Adaptation | 2 | B | 1
2 | Functional Review | 3 | B | 1
2 | UAT | 4 | B | 1
2 | Training | 5 | B | 2
2 | DIALT | 6 | B | 1
2 | Go Live | 7 | B | 1
2 | Hypercare | 8 | B | 4
3 | Site Readiness | 1 | B | 4
3 | Design Adaptation | 2 | B | 1
3 | Functional Review | 3 | B | 1
3 | UAT | 4 | B | 1
3 | Training | 5 | B | 2
3 | DIALT | 6 | B | 1
3 | Go Live | 7 | B | 1
3 | Hypercare | 8 | B | 4
4 | Site Readiness | 1 | B | 2
4 | Design Adaptation | 2 | B | 0
4 | Functional Review | 3 | B | 1
4 | UAT | 4 | B | 1
4 | Training | 5 | B | 1
4 | DIALT | 6 | B | 1
4 | Go Live | 7 | B | 1
4 | Hypercare | 8 | B | 3

## Phase-Resource Allocation
Cluster | Phase | Role | Capacity Consumption
1 | Site Readiness | Infrastructure Lead | 100%
1 | Site Readiness | SAP Integrations Lead | 50%
1 | Design Adaptation | Solution Architect | 100%
1 | Design Adaptation | SAP Integrations Lead | 50%
1 | Design Adaptation | SAP Integrations Specialist | 50%
1 | Design Adaptation | Azure Lead | 50%
1 | Design Adaptation | Azure Specialist | 50%
1 | Design Adaptation | Testing Lead | 100%
1 | Design Adaptation | Functional Lead | 100%
1 | Design Adaptation | Trainers | 100%
1 | Design Adaptation | Infrastructure Lead | 100%
1 | Design Adaptation | Functional Lead Vendor A | 100%
1 | Functional Review | Solution Architect | 50%
1 | Functional Review | Change Management Lead | 100%
1 | Functional Review | SAP Integrations Lead | 50%
1 | Functional Review | SAP Integrations Specialist | 50%
1 | Functional Review | Azure Lead | 50%
1 | Functional Review | Azure Specialist | 50%
1 | Functional Review | Testing Lead | 50%
1 | Functional Review | Functional Lead | 100%
1 | Functional Review | Trainers | 100%
1 | UAT | Solution Architect | 50%
1 | UAT | Change Management Lead | 100%
1 | UAT | SAP Integrations Lead | 50%
1 | UAT | SAP Integrations Specialist | 50%
1 | UAT | Azure Lead | 50%
1 | UAT | Azure Specialist | 50%
1 | UAT | Testing Lead | 50%
1 | UAT | Functional Lead | 100%
1 | UAT | Trainers | 100%
1 | Training | Change Management Lead | 100%
1 | Training | Trainers | 100%
1 | DIALT | Solution Architect | 50%
1 | DIALT | Change Management Lead | 100%
1 | DIALT | Azure Lead | 75%
1 | DIALT | Azure Specialist | 75%
1 | DIALT | Functional Lead | 100%
1 | DIALT | Trainers | 100%
1 | DIALT | Functional Lead Vendor A | 100%
1 | Go Live | Solution Architect | 100%
1 | Go Live | Change Management Lead | 100%
1 | Go Live | SAP Integrations Lead | 100%
1 | Go Live | SAP Integrations Specialist | 100%
1 | Go Live | Azure Lead | 100%
1 | Go Live | Azure Specialist | 100%
1 | Go Live | Functional Lead | 100%
1 | Go Live | Trainers | 100%
1 | Go Live | Infrastructure Lead | 100%
1 | Go Live | Functional Lead Vendor A | 100%
1 | Hypercare | Solution Architect | 50%
1 | Hypercare | Change Management Lead | 100%
1 | Hypercare | SAP Integrations Lead | 50%
1 | Hypercare | SAP Integrations Specialist | 50%
1 | Hypercare | Azure Lead | 50%
1 | Hypercare | Azure Specialist | 50%
1 | Hypercare | Functional Lead | 100%
1 | Hypercare | Functional Lead | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Infrastructure Lead | 100%
1 | Hypercare | Functional Lead Vendor A | 50%
2 | Site Readiness | Infrastructure Lead | 100%
2 | Site Readiness | SAP Integrations Lead | 50%
2 | Design Adaptation | Solution Architect | 100%
2 | Design Adaptation | SAP Integrations Lead | 50%
2 | Design Adaptation | SAP Integrations Specialist | 50%
2 | Design Adaptation | Azure Lead | 50%
2 | Design Adaptation | Azure Specialist | 50%
2 | Design Adaptation | Testing Lead | 100%
2 | Design Adaptation | Functional Lead | 100%
2 | Design Adaptation | Trainers | 100%
2 | Design Adaptation | Infrastructure Lead | 100%
2 | Design Adaptation | Functional Lead Vendor A | 100%
2 | Functional Review | Solution Architect | 50%
2 | Functional Review | Change Management Lead | 100%
2 | Functional Review | SAP Integrations Lead | 50%
2 | Functional Review | SAP Integrations Specialist | 50%
2 | Functional Review | Azure Lead | 50%
2 | Functional Review | Azure Specialist | 50%
2 | Functional Review | Testing Lead | 50%
2 | Functional Review | Functional Lead | 100%
2 | Functional Review | Trainers | 100%
2 | UAT | Solution Architect | 50%
2 | UAT | Change Management Lead | 100%
2 | UAT | SAP Integrations Lead | 50%
2 | UAT | SAP Integrations Specialist | 50%
2 | UAT | Azure Lead | 50%
2 | UAT | Azure Specialist | 50%
2 | UAT | Testing Lead | 50%
2 | UAT | Functional Lead | 100%
2 | UAT | Trainers | 100%
2 | Training | Change Management Lead | 100%
2 | Training | Trainers | 100%
2 | DIALT | Solution Architect | 50%
2 | DIALT | Change Management Lead | 100%
2 | DIALT | Azure Lead | 75%
2 | DIALT | Azure Specialist | 75%
2 | DIALT | Functional Lead | 100%
2 | DIALT | Trainers | 100%
2 | DIALT | Functional Lead Vendor A | 100%
2 | Go Live | Solution Architect | 100%
2 | Go Live | Change Management Lead | 100%
2 | Go Live | SAP Integrations Lead | 100%
2 | Go Live | SAP Integrations Specialist | 100%
2 | Go Live | Azure Lead | 100%
2 | Go Live | Azure Specialist | 100%
2 | Go Live | Functional Lead | 100%
2 | Go Live | Trainers | 100%
2 | Go Live | Infrastructure Lead | 100%
2 | Go Live | Functional Lead Vendor A | 100%
2 | Hypercare | Solution Architect | 50%
2 | Hypercare | Change Management Lead | 100%
2 | Hypercare | SAP Integrations Lead | 50%
2 | Hypercare | SAP Integrations Specialist | 50%
2 | Hypercare | Azure Lead | 50%
2 | Hypercare | Azure Specialist | 50%
2 | Hypercare | Functional Lead | 100%
2 | Hypercare | Functional Lead | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Infrastructure Lead | 100%
2 | Hypercare | Functional Lead Vendor A | 50%
3 | Site Readiness | Infrastructure Lead | 100%
3 | Site Readiness | SAP Integrations Lead | 50%
3 | Design Adaptation | Solution Architect | 100%
3 | Design Adaptation | SAP Integrations Lead | 50%
3 | Design Adaptation | SAP Integrations Specialist | 50%
3 | Design Adaptation | Azure Lead | 50%
3 | Design Adaptation | Azure Specialist | 50%
3 | Design Adaptation | Testing Lead | 100%
3 | Design Adaptation | Functional Lead | 100%
3 | Design Adaptation | Trainers | 100%
3 | Design Adaptation | Infrastructure Lead | 100%
3 | Design Adaptation | Functional Lead Vendor A | 100%
3 | Functional Review | Solution Architect | 50%
3 | Functional Review | Change Management Lead | 100%
3 | Functional Review | SAP Integrations Lead | 50%
3 | Functional Review | SAP Integrations Specialist | 50%
3 | Functional Review | Azure Lead | 50%
3 | Functional Review | Azure Specialist | 50%
3 | Functional Review | Testing Lead | 50%
3 | Functional Review | Functional Lead | 100%
3 | Functional Review | Trainers | 100%
3 | UAT | Solution Architect | 50%
3 | UAT | Change Management Lead | 100%
3 | UAT | SAP Integrations Lead | 50%
3 | UAT | SAP Integrations Specialist | 50%
3 | UAT | Azure Lead | 50%
3 | UAT | Azure Specialist | 50%
3 | UAT | Testing Lead | 50%
3 | UAT | Functional Lead | 100%
3 | UAT | Trainers | 100%
3 | Training | Change Management Lead | 100%
3 | Training | Trainers | 100%
3 | DIALT | Solution Architect | 50%
3 | DIALT | Change Management Lead | 100%
3 | DIALT | Azure Lead | 75%
3 | DIALT | Azure Specialist | 75%
3 | DIALT | Functional Lead | 100%
3 | DIALT | Trainers | 100%
3 | DIALT | Functional Lead Vendor A | 100%
3 | Go Live | Solution Architect | 100%
3 | Go Live | Change Management Lead | 100%
3 | Go Live | SAP Integrations Lead | 100%
3 | Go Live | SAP Integrations Specialist | 100%
3 | Go Live | Azure Lead | 100%
3 | Go Live | Azure Specialist | 100%
3 | Go Live | Functional Lead | 100%
3 | Go Live | Trainers | 100%
3 | Go Live | Infrastructure Lead | 100%
3 | Go Live | Functional Lead Vendor A | 100%
3 | Hypercare | Solution Architect | 50%
3 | Hypercare | Change Management Lead | 100%
3 | Hypercare | SAP Integrations Lead | 50%
3 | Hypercare | SAP Integrations Specialist | 50%
3 | Hypercare | Azure Lead | 50%
3 | Hypercare | Azure Specialist | 50%
3 | Hypercare | Functional Lead | 100%
3 | Hypercare | Functional Lead | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Infrastructure Lead | 100%
3 | Hypercare | Functional Lead Vendor A | 50%